## HLP
High Level Plan for CAI Initiative
[56 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
 | time axis 2014-04-21 to 2059-07-14
[88 empty] | All the trainees to attend XTSummit from 2 pm | [19 empty] | Public Holiday ¦¦ X-MAS | [31 empty] | Public Holiday ¦¦ Republic Day
Demo by Trainees on Cloud
Vendor Finalization as a Trainer
Demo of a Trainer/ Make it More Sapientized
Based on the content Prepare Mock Project
Create Tools/Templates for Project
Create Post Project Assessment Phase - I along with the % weightage. (Identify Low Performers and decide their next steps)
Include Adv Learnings in the same project from Phase 1 in the phase 2 Project and Create Assessment with the % weightage (Low Performerns Vs Top Performers)
Sape Start
ILT Session - Basic Web Programming
Project Assessment Phase - I
ILT Session - Advance Web Programming
Project Assessment Phase - II
They are Here
Development Phase - 11.5 Days
Demo by Trainees on Cloud
Project Walkthrough / Ramp up/Requirement Gathering/ Develpment
QA/Functional & Bug Fixing
Development Phase - 12 Days
Soft skills with Assessment
QA/Functional & Bug Fixing

## Mentor Connect (hidden)
Date | GGN Mentor | Gurgaon | Bangalore Mentor | Bangalore
2014-06-24 | Raman Mehta/ Vandana Gupta | 3.30pm - 4.30pm | Sridhar KN/ Sajan John | 3pm - 4pm
2014-07-01 | Kumar Gaurav | 3.30pm - 4.30pm | Sreejesh Karunakaran/ Amalan W George | 3pm - 4pm
2014-07-08 | Ravi Pal | 3.30pm - 4.30pm | Prasanna Venkatesh/Sridhar KN | 3pm - 4pm
2014-08-05 | Vandana Gupta/ Ankit Singhal | 3.30pm - 4.30pm | Parag Gajjar/Sajan John | 3pm - 4pm
2014-08-12 | Sailesh Raghavan | 3.30pm - 4.30pm | Nitya Krishnamoorthy/ Giri Jeedigunta | 3pm - 4pm
2014-08-26 | Mayank Singhal/Anoop K Gupta | 3.30pm - 4.30pm | Sreejesh Karunakaran/Nitya Krishnamoorthy | 3pm - 4pm
2014-09-02 | Ritesh Batra/ Vikash Bhardwaj | 3.30pm - 4.30pm | Giri Jeedigunta/Amalan W George | 3pm - 4pm

## Notes (hidden)
Task | Owner | Due Date | Status | Artifacts To Be Used | Comments
Create HLP | Ankita | 2014-08-21 | Completed
HLP Validated by Vikash Bhardwaj | Vikash | 2014-08-21 | Completed
Create SOD on the basis of our requirements | Vikash |  |  |  | Assuming Bangalore is on same page
Create LLP for the 10 days based on our SOD | Vikash/Prasanna | 2014-08-22 | In Progress
Update Requirement document based on the new functionalities from Sailesh | Ankita/Neha | 2014-08-21 | In Progress
Get PSD's created | Ankita/Neha | 2014-08-22 | Open
Identify who can do QA for us | Ankita/Neha | 2014-08-22 | Open
Need information around Cloud Environment which wil be used to do our Build on the 10 Sept | Ankita/Neha | 2014-08-22 | Open |  | Incase anyone form our group knows anything around this environment please help me on how to do this