## Title
Consolidated CAI Tracker Steps of Doneness - Phase II

## Track Snapshot
Site Dev Progress |  |  | Build Progress
|  |  | Build Date | (All)
Story Count |  |  | Average of % Complete
Project Name | Status By Individuals | Total | Project Name | Owner Name | Story | Total
Asset_Tracker | Not Started | 2 | Asset_Tracker | Neha | Login Page | 92%
| Completed | 13 |  |  | Registeration Page - Functional | 79%
| In Progress | 12 |  |  | Request a new device if doesn't exist - This should be part of Request a device page only. - Design the page - Functionality of page | 92%
Feedback_Tracker | Started | 1 |  | Promil | Instructions - Design only | 77%
| Completed | 5 |  |  | Add new Accessories - Design - Funcationality | 32.7%
| In Progress | 10 |  |  | Remove Device and Remove Accessories: - Design the Page - Functional for Remove accessories | 32.7%
(blank) | (blank) |  |  |  | Add Upcoming Device/Accessories - Design the page - Functionality of page | 64%
Prob_Form | Not Started | 1 |  |  | Add Lost Devices/Accessories - Design the page - Functionality of page | 64%
| Completed | 12 |  |  | Add new Device - Functionality | 64%
| In Progress | 14 |  | Umang | Dashboard home page * Design * Edit Account Details | 87%
Grand Total |  | 70 |  |  | Pending Request Page: - Design the Page - Pending back-end integration | 77%
[5 empty] | User history page wrt devices usage - Design the Page - Pending back-end integration | 42.35%
|  |  |  | Rahul | Registeration Page - Design | 85%
[5 empty] | Device List - Design + Actual service integeration | 50.6%
[5 empty] | My Account * Change Password - Functional + Design * Forgot Password - Functional + Design | 74%
|  |  |  | Pratibha | Carousel on Home Page - Design - Funcationality | 88%
[5 empty] | Pending Requests for Devices/Accessories - Design page - Functionality of page | 68.7%
[5 empty] | Alert for Long time pending requests - Design Dialog and page - Functionality of complete alert flow | 0%
[5 empty] | Request Extension for device - Design the Page - Pending back-end integration | 18.2%
|  |  |  | Abhishek | Add new Device - Design | 20%
[5 empty] | Profile Detail page - For Admin to see the complete detail for user whom the device is allocated. - Design the Page - Functionality of Page | 64%
[5 empty] | Device history - Design + Actual service integeration - Page design for existing pages and pending requests for device page. | 72%
[5 empty] | Search Page - Design the Page | 64%
|  |  |  | Kuldeep | Logout/Thank You Page - Design the Page | 0%
[5 empty] | Request Device/Accessories - Design the Page - Pending back-end integration | 57%
[5 empty] | Remove existing Request from their list: Please make sure request shouldn't be deleted from system and it should be in some kind of disabled state. These request in admin panel should be at end in the results. - Design the Page - Pending back-end integr | 37.8%
[5 empty] | Report Chart - Device Usage for Admin - Design the Page - Functionality of Page | 32%
|  |  | Feedback_Tracker | Deepika | My Account - Design the Page | 100%
[5 empty] | Candidate listing/Search Page - Design the Page - Functionality of Page | 64.3%
[5 empty] | Feedback History Page - Design the Page - Functionality of Page | 64.3%
[5 empty] | Candidate Feedback Page(Super Admin can see all the feedbacks) - Design the Page - Functionality of Page | 81.3%
|  |  |  | Akash | My Account - Edit Account - Functionality | 60%
[5 empty] | Appreciation and Feedback for top performer or laggards from Listing - Design the Page/Dialog - Functionality of Page | 70%
|  |  |  | Praveen | Login Page | 80%
[5 empty] | Request Feedback Page for user from SA: - Design the Page - Functionality of Page | 70%
[5 empty] | Request Feedback Page for Candidate from project PM or to any individual. - Design the Page - Functionality of Page | 0%
[5 empty] | Pending feedback requests page - Design the Page - Functionality of Page | 0%
|  |  |  | Divya | Registeration Page - Design | 100%
[5 empty] | Registeration Page - Functional | 100%
[5 empty] | Forgot Password | 100%
[5 empty] | Superadmin can approve or reject user - Design the Page - Functionality of Page | 52.6%
|  |  |  | Shubhra | Provide Feedback Page - Page will be used to provide the feedback for any asked user/candidate. - Design the Page | 51.6%
[5 empty] | Provide Feedback Page - Page will be used to provide the feedback for any asked user/candidate. - Functionality of Page | 37.6%
|  |  | Prob_Form | Rashi | Login Page | 80.8%
[5 empty] | Registeration Page - Design | 94.9%
[5 empty] | Create Skill set level Matrix Page - Functionality of Page | 74.6%
|  |  |  | Piyush | Registeration Page - Functional | 0%
[5 empty] | Take Test - Design the Page | 0%
[5 empty] | Take Test - Functionality of Page | 0%
|  |  |  | Anil | Logout/Thank You Page - Design the Page | 0%
[5 empty] | Candidate Listing Page for HR/Interviewer and same will be available to SA at any time - Design the Page | 100%
[5 empty] | Create/Modify Questions - Functionality of Page | 79%
[5 empty] | Create Skill set level Matrix Page - Design the Page | 65.1%
|  |  |  | Arushi | My account | 80.9%
[5 empty] | My Account * Change Password - Functional + Design * Forgot Password - Functional + Design | 83%
|  |  |  | Kajal | Manage Request Page - SA - Design the Page - Functionality of page | 75%
[5 empty] | Create/Modify Questions - Design the Page | 85%
[5 empty] | Create Modal popup - Design the Page | 100%
|  |  |  | Ankit | Interviewer/HR Listing Page - for SA - Design the Page - Functionality of Page | 0%
[5 empty] | Candidate Listing Page for HR and same will be available to SA at any time - Functionality of Page | 90.4%
|  |  |  | Satyam | Create/Define Category Page - Design the Page - Functionality of Page | 90%
[5 empty] | Register Candidate - Design the Page - Functionality of Page | 90%
[5 empty] | Guideline/Instructions - Design the Page - Functionality of Page | 90%
|  |  |  | Gaurav | Candidate Listing Page for Interviewer and same will be available to SA at any time - Functionality of Page | 92%
[5 empty] | Probe Form Provide Feedback Page - Design the Page | 43%
|  |  |  | Raunak | Probe Form Provide Feedback Page - Functionality of Page | 76%
[5 empty] | Candidate Result Page - Design the Page - Functionality of Page | 100%
|  |  |  | Kunal | Dashboard for Super Admin/ Admin | 84.5%
[5 empty] | Skill Level Matrix Page - Design the Page | 0%
[5 empty] | Skill Level Matrix Page - Functionality of Page | 0%

## Sheet1 (hidden)
Milestones and Dep
Milestones / Dependencies | Due Date | Owners | Status | If not complete, new due date
Milestones / Dependencies past due date
Review Design of Portal with iCrossing | 2010-09-17 08:00 | Graham
Copy Deck Complete | 2010-09-30 08:00 | Graham
Flash Development Specification complete | 2010-09-13 08:00 | Graham
Wireframes and Comps updated and signed off | 2010-09-24 08:00 | Graham
Mobile Signatures closed with Mobile Vendor | 2010-09-17 17:00 | Sarvesh
Musical Artist Name and Anthem Song | 2010-09-20 08:00 | Graham
SearchRev tagging structure provided to Sapient | 2010-09-24 17:00 | Graham
SEO strategy closed - iCrossing to provide deck | 2010-09-24 08:00 | John
Milestones / Dependencies due TODAY
Market Activation Guide Complete | 2010-10-01 17:00 | Graham
Scope Matrix updated and Signed off | 2010-10-01 17:00 | Graham
CMS Content Assessment Complete | 2010-10-01 08:00 | Graham
CMS Profile Setup | 2010-10-01 08:00 | John
WebTrends Profile Setup | 2010-10-01 08:00 | Sarvesh
Milestones / Dependencies due next week
Pilot Markets Identified | 2010-10-04 08:00 | John
Fair Issac Profile Setup | 2010-10-04 08:00 | Graham
Milestones / Dependencies due next to next week
Send SMS service available | 2010-10-11 08:00 | Sarvesh
Savvis Test Infrastructure Setup | 2010-10-11 17:00 | Sarvesh
First deployment to Savvis | 2010-10-12 17:00 | Sarvesh
Mobile App available for Integration in Savis Environment | 2010-10-11 08:00 | Sarvesh

## Site Dev_SOD
Consolidated SOD
Project Name | Ref. No | Story | Milestones for Story | Category | Owner Name | Start Date | End Date | Estimated New End date | Status By Individuals | Build Date | % Complete | Complexity Level | Total LOE in days (ABP) | LOE Left to Complete(Days) | Actual LOE | Sync-up with Track Lead & Back end Developer to discuss Story Deliverables | Review Wireframes, Visuals/Styleguides | Raise any risks/issue /dependencies | Create HTML | Create CSS | Write Java Script | Visual Comps Incorporation | Analytics(Omniture or Any Other) | Validate JS code with JSLint | W3C Validation | Page Tested using Total Validator for Accessibility(Level A) and W3C Errors | Test on IE 11 | Test on Chrome | Test on Firefox 3.6+ | Test on Safari 3 (Win, MAC) | Test on Android | Test on IOS | Internal Review | Review Comments Incorporation | Integration Status with PHP Integrated Code Review | External Review | Review Comments Incorporation | Delivered Quality (Self-Assessment) | Comments / Remarks
[6 empty] | 2014-09-05 | 2014-09-05 |  | Completed |  | 100% |  | 1.5 |  |  | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 10000% | 100
Asset_Tracker | 1 | Login Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Neha | 2014-09-03 | 2014-09-04 |  | Completed |  | 100% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 2 | Registeration Page - Design | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Rahul | 2014-09-03 | 2014-09-04 |  | Completed |  | 100% |  | 2.5 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 3 | Registeration Page - Functional | * Error Messages/ Validations should work fine and backend functionality should be implemented with actual backend services |  | Neha | 2014-09-03 | 2014-09-03 |  | Not Started |  | 0% |  | 1
Asset_Tracker | 4 | Logout/Thank You Page - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * User should be able to logout and come to Login page. |  | Kuldeep | 2014-09-08 | 2014-09-10 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 5 | My Account * Change Password - Functional + Design * Forgot Password - Functional + Design | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Logged in user should be able to change the password * User should be able to use forgot password feature to change the password * Form Validations |  | Rahul | 2014-09-03 | 2014-09-05 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 6 | Dashboard home page * Design * Edit Account Details | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Edit Account detail should be implemented |  | Umang | 2014-09-08 | 2014-09-10 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 7 | Carousel on Home Page - Design - Funcationality | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Carousel should work fine with Thumbnails and their respective details. |  | Pratibha | 2014-09-03 | 2014-09-04 |  | Completed |  | 100% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 8 | Device List - Design + Actual service integeration | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Column based sorting |  | Rahul | 2014-09-08 | 2014-09-10 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 9 | Profile Detail page - For Admin to see the complete detail for user whom the device is allocated. - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to see the User detail in a dialog . * This dialog will open on click of User Name to whom the device is assigned. |  | Abhishek | 2014-09-03 | 2014-09-05 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 41890 | 41737
Asset_Tracker | 10 | Instructions - Design only | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Promil | 2014-09-08 | 2014-09-10 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 11 | Device history - Design + Actual service integeration - Page design for existing pages and pending requests for device page. | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin/User should be able to see all the pending requests for that device. |  | Abhishek | 2014-09-08 | 2014-09-10 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 12 | Add new Device - Design | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Abhishek | 2014-09-08 | 2014-09-09 |  | Completed |  | 100% |  | 2.5 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 13 | Add new Accessories - Design - Funcationality | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to add accessories into system. |  | Promil | 2014-09-10 | 2014-09-10 |  | Completed |  | 100% |  | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 14 | Remove Device and Remove Accessories: - Design the Page - Functional for Remove accessories | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to remove accessories from system. |  | Promil | 2014-09-05 | 2014-09-09 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 15 | Add Upcoming Device/Accessories - Design the page - Functionality of page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to add New devices in system which will be used for Carousel. |  | Promil | 2014-09-03 | 2014-09-04 |  | Completed |  | 100% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 16 | Add Lost Devices/Accessories - Design the page - Functionality of page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to add info for Lost devices/accessories in system which will be used for Carousel. |  | Promil | 2014-09-09 | 2014-09-09 |  | Completed |  | 100% |  | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 17 | Pending Requests for Devices/Accessories - Design page - Functionality of page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to allocate and de-allocate devices as per pending request. |  | Pratibha | 2014-09-10 | 2014-09-11 |  | Completed |  | 100% |  | 2.5 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 18 | Alert for Long time pending requests - Design Dialog and page - Functionality of complete alert flow | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to send the request to requester for long pending items asking if they still need device and if yes ask them to extend the request. * Please refer requirement doc for detailed requirement. |  | Pratibha | 2014-09-10 | 2014-09-11 |  | Completed |  | 100% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 19 | Request a new device if doesn't exist - This should be part of Request a device page only. - Design the page - Functionality of page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * User should be able to request a new devices which is not in inventory. * Please refer requirement DOC for detailed Milestone. |  | Neha | 2014-09-09 | 2014-09-10 |  | Completed |  | 100% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 20 | Request Device/Accessories - Design the Page - Pending back-end integration | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * User should be able to request a new device. |  | Kuldeep | 2014-09-03 | 2014-09-05 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1900-04-09
Asset_Tracker | 21 | Pending Request Page: - Design the Page - Pending back-end integration | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * User should be able to see their pending requests for devices. |  | Umang | 2014-09-03 | 2014-09-05 |  | Completed |  | 100% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 22 | User history page wrt devices usage - Design the Page - Pending back-end integration | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * User should be able to see their devices used history. |  | Umang | 2014-09-03 | 2014-09-08 |  | Completed |  | 100% |  | 4 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 23 | Request Extension for device - Design the Page - Pending back-end integration | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * User should be able to request extension for a device already assigned. |  | Pratibha | 2014-09-05 | 2014-09-05 |  | Completed |  | 100% |  | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 24 | Remove existing Request from their list: Please make sure request shouldn't be deleted from system and it should be in some kind of disabled state. These request in admin panel should be at end in the results. - Design the Page - Pending back-end integration | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * User should be able to terminate request. |  | Kuldeep | 2014-09-10 | 2014-09-11 |  | Completed |  | 100% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 25 | Report Chart - Device Usage for Admin - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to see the Devices usage chart. |  | Neha | 2014-09-05 | 2014-09-05 |  | Completed |  | 100% |  | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 26 | Search Page - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin should be able to see the Search results. |  | Abhishek | 2014-09-08 | 2014-09-09 |  | Completed |  | 100% |  | 2.5 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Asset_Tracker | 12 | Add new Device - Functionality | * Create form * Create form validations * Submit data to the server * Add asset details as per the design shared on psd's |  | Promil | 2014-09-12 | 2014-09-12 |  | Completed |  | 145000% |  | 1.5 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 50 | 100 |  | 100 | 100 | 100 |  |  |  | 100 | 100 |  | 100 | 100
Feedback_Tracker | 1 | Login Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Praveen | 2014-09-03 | 2014-09-03 |  | In Progress |  | 80% |  | 1 |  |  | 80 | 100 | 100 | 100 | 100 | 80
Feedback_Tracker | 2 | Registeration Page - Design | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Divya | 2014-09-03 | 2014-09-04 |  | Completed |  | 100% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | [5 empty] | 100 | 100 | 100 | 100
Feedback_Tracker | 3 | Registeration Page - Functional | * Admin/HR/Supervisor should be able to request SA for approving the request on their account. * SA and Admin/HR/Supervisor should get email notifications for request and approval respectively. |  | Divya | 2014-09-05 | 2014-09-08 |  | Completed |  | 100% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | [5 empty] | 100 | 100 | 100 | 100
Feedback_Tracker | 4 | Forgot Password | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * user should be able to change password. |  | Divya | 2014-09-03 | 2014-09-03 |  | Completed |  | 100% |  | 0.5 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | [5 empty] | 100 | 100 | 100 | 100
Feedback_Tracker | 5 | Appreciation and Feedback for top performer or laggards from Listing - Design the Page/Dialog - Functionality of Page | * SA should be able to send appreciation or feedback respectively to candidates. * Candidate should get email notification for this feedback. * There should be a way by which SA should be able to see how many appreciation has been provided by him/her with names clubbed in an accordion. |  | Akash | 2014-09-03 | 2014-09-05 |  | In Progress |  | 70% |  | 3 |  |  | 100 | 100 | 100 | 100 | 90 | 80 | 100 | 100 |  |  |  | 50 | 100 | 90 | 50
Feedback_Tracker | 6 | My Account - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Deepika | 2014-09-03 | 2014-09-04 |  | Completed |  | 100% |  | 2.5 |  |  | 100 | 100 | 100 | 100 | 90 | 0 | 100 | 100 |  |  |  | 90 | 100 | 90 | 100
Feedback_Tracker | 7 | My Account - Edit Account - Functionality | * Admin/HR/Supervisor should be able to edit their account information. |  | Akash | 2014-09-09 | 2014-09-10 |  | In Progress |  | 60% |  | 2 |  |  | 100 | 100 | 100 | 100 | 90 | 70 | 100 | 100 |  |  |  | 50 | 100 | 90 | 50
Feedback_Tracker | 8 | Request Feedback Page for user from SA: - Design the Page - Functionality of Page | * Admin/HR/Supervisor should be able to request for candidate feedback from SA in case he/she is not eligible to see feedback for an individual. |  | Praveen | 2014-09-04 | 2014-09-04 |  | In Progress |  | 70% |  | 1 |  |  | 80 | 100 | 100 | 100 | 100 | 100
Feedback_Tracker | 9 | Request Feedback Page for Candidate from project PM or to any individual. - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin/HR/Supervisor should be able to request feedback for any individual from project PM or any individual. *Save as draft functionality * Admin/HR/Supervisor should be able to request feedback only for registered users/candidates. |  | Praveen | 2014-09-05 | 2014-09-08 |  | Started |  | 0% |  | 2 |  |  | 0 | 0 | 0 | 0 | 0
Feedback_Tracker | 10 | Provide Feedback Page - Page will be used to provide the feedback for any asked user/candidate. - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Shubhra | 2014-09-03 | 2014-09-05 |  | In Progress |  | 95000% |  | 3 |  |  | 100 | 100 | 100 | 100 | 90 | 0 | 100 |  |  |  |  | 90 | 90 | 90 | 90
Feedback_Tracker | 11 | Provide Feedback Page - Page will be used to provide the feedback for any asked user/candidate. - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Project PM or any individual whom has been requested to provide feedback should be able to access this feedback page through link from email generated from Request feedback page process. * Project PM or any individual whom has been requested to provide feedback should be able to save the half feedback as "save for later" and then can continue the same at some point of time later. * Once Project PM or any individual whom has been requested to provide feedback should be able to submit Feedback and Admin/HR/Supervisor should get email noification for feedback submission. * Project PM or any individual whom has been requested to provide feedback should see message "Already feedback provided for this request" for already submitted feedback from that link. |  | Shubhra | 2014-09-08 | 2014-09-10 |  | Completed |  | 76000% |  | 3.5 |  |  |  | 100 | 100 | 0 | 0 | 100 | 100 |  |  |  |  | 90 | 90 | 90 | 90
Feedback_Tracker | 12 | Candidate listing/Search Page - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * List of Candidates with options for going to candidate feedback page. * Admin/HR/Supervisor should be able to see only allowed users. * Logged In user should be able to sort the records by multiple fields. |  | Deepika | 2014-09-08 | 2014-09-09 |  | In Progress |  | 114000% |  | 2.5 |  |  | 100 | 100 | 100 | 100 | 80 | 80 | 100 | 100 |  |  |  | 90 | 100 | 90 | 100
Feedback_Tracker | 13 | Candidate Feedback Page(Super Admin can see all the feedbacks) - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Superadmin should be able to see all feedback. |  | Deepika | 2014-09-10 | 2014-09-11 |  | In Progress |  | 145000% |  | 2 |  |  | 100 | 100 | 100 | 100 | 90 | 100 | 100 | 100 |  | 10 | 10 | 80 | 80 | 80 | 80 | 10 | 10 | 100 | 100 | 100 | 100 | 70 | 60
Feedback_Tracker | 14 | Pending feedback requests page - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports *SuperAdmin can approve any requested feedback |  | Praveen | 2014-09-11 | 2014-09-11 |  | In Progress |  | 0%
Feedback_Tracker | 15 | Superadmin can approve or reject user - Design the Page - Functionality of Page | Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports *Superadmin can approve or decline the user |  | Divya | 2014-09-12 | 2014-09-15 |  | In Progress |  | 96000% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | [5 empty] | 90 | 90 | 90 | 90
Feedback_Tracker | 16 | Feedback History Page - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Admin/HR/Supervisor should be able to see feedback hostory page. |  | Deepika | 2014-09-04 | 2014-09-05 |  | In Progress |  | 114000% |  | 2 |  |  | 100 | 100 | 100 | 100 | 80 | 80 | 100 | 100 |  |  |  | 90 | 100 | 90 | 100
Prob_Form | 1 | Login Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Rashi | 2014-09-05 | 2014-09-05 |  | In Progress |  | 163000% |  | 1.5 |  |  | 100 | 100 | 100 | 100 | 90 | 90 | 100 | 100 | 100 |  |  | 90 | 90 | 90 | 100 | 100 | 100 | 90 | 90
Prob_Form | 2 | Registeration Page - Design | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Rashi | 2014-09-03 | 2014-09-04 |  | Completed |  | 179800% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 98 | 100
Prob_Form | 3 | Registeration Page - Functional | * Admin/HR/Interviewer should be able to request SA for approving the request on their account. * SA and Admin/HR/Interviewer should get email notifications for request and approval respectively. |  | Piyush | 2014-09-03 | 2014-09-04 |  | Completed |  | 200000% |  | 2.5 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 4 | Logout/Thank You Page - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * User should be able to logout and come to Login page. |  | Anil | 2014-09-03 | 2014-09-03 |  | Not Started |  | 0% |  | 1
Prob_Form | 5 | My Account * Change Password - Functional + Design * Forgot Password - Functional + Design | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Logged in user should be able to change the password * User should be able to use forgot password feature to change the password * Form Validations |  | Arushi | 2014-09-08 | 2014-09-10 |  | In Progress |  | 170000% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 50 | 90 | 90 |  | 100 | 100 | 100 | 100 | 100 | 60 | 60 | 100
Prob_Form | 7 | Interviewer/HR Listing Page - for SA - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * SA should be able to see the HR/Interviewer List and there should be a flag for each row to indicate if the profile is HR or Interviewer. |  | Ankit | 2014-09-03 | 2014-09-05 |  | Completed |  | 0% |  | 3
Prob_Form | 8 | Create/Define Category Page - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * SA should be able to define/create the New categories in system for different profiles like HR, Interviewer along with their permissions. |  | Satyam | 2014-09-08 | 2014-09-10 |  | Completed |  | 170000% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 41893 | 41893 |  | Vijayendra Kumar did the Code Review. Code review incorporations have been done.
Prob_Form | 9 | Candidate Listing Page for HR/Interviewer and same will be available to SA at any time - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Anil | 2014-09-03 | 2014-09-04 |  | Completed |  | 200000% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 10 | Candidate Listing Page for HR and same will be available to SA at any time - Functionality of Page | * HR can select from the list of candidates, new candidates will be listed on top of the list. * HR can do a list search and sort and re-order from the list. * HR should be able to see pre online test results for the candidates from the list. * HR can assign the candidates to the registered Interviewer. |  | Ankit | 2014-09-08 | 2014-09-10 |  | In Progress |  | 184000% |  | 3 |  |  | 100 | 100 | 100 | 100 | 50 | 100 | 100 | 100 | 70 | 70 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 70 | 80 | 100
Prob_Form | 11 | Candidate Listing Page for Interviewer and same will be available to SA at any time - Functionality of Page | * Interviewer can select from the list of candidates, latest assigned candidate will be listed on top of the list. * Interviewer can do a list search and sort and re-order from the list. * Interviewer should be able to see pre online test results for the candidates from the list. |  | Gaurav | 2014-09-03 | 2014-09-05 |  | Completed |  | 180000% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 41890 | 41737
Prob_Form | 12 | Probe Form Provide Feedback Page - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Gaurav | 2014-09-08 | 2014-09-10 |  | In Progress |  | 68000% |  | 3 |  |  | 100 | 100 | 100 | 40 | 40 | 100 | 100 |  | 100
Prob_Form | 13 | Probe Form Provide Feedback Page - Functionality of Page | * Interviewer can provide the feedback or initiate the feedback filling process, from the probe form page. * Interviewer can save the half filled Feedback form for later submission. * Requirement document has the detailed out fields name which is needed while sending the feedback by Interviewer. * Refer to requirement document for probe form feedback format. |  | Raunak | 2014-09-08 | 2014-09-10 |  | In Progress |  | 156000% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 60 | 100 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 14 | Create/Modify Questions - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Kajal | 2014-09-08 | 2014-09-09 |  | Completed |  | 170000% |  | 2.5 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 14 | Create Modal popup - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Kajal | 2014-09-10 | 2014-09-10 |  | Completed |  | 200000% |  | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 14 | Create/Modify Questions - Functionality of Page | * Admin/Interviewer can create and modify there posted question later. * Once admin modify the question, the question will be disabled, and our application will not be able to use it till the time SA does'nt approve it. |  | Anil | 2014-09-05 | 2014-09-09 |  | In Progress |  | 159000% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 90 | 100 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 15 | Register Candidate - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * HR should be able to register candidate for test, on successful registration send an email to the candidates. |  | Satyam | 2014-09-03 | 2014-09-04 |  | In Progress |  | 170000% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 16 | Skill Level Matrix Page - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Kunal | 2014-09-09 | 2014-09-09 |  | In Progress |  | 0% |  | 1
Prob_Form | 16 | Skill Level Matrix Page - Functionality of Page | * Interviewer/HR should be able to see the Skill Level Matrix. * This matrix should be implemented with dynamic data. |  | Kunal | 2014-09-10 | 2014-09-11 |  | In Progress |  | 0% |  | 2.5
Prob_Form | 17 | Create Skill set level Matrix Page - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports |  | Anil | 2014-09-10 | 2014-09-11 |  | In Progress |  | 128000% |  | 2 |  |  | 100 | 100 | 100 | 60 | 60 | 100 | 100 | 100 |  |  | 100 | 30 | 100 | 30 | 100 | 100 | 100
Prob_Form | 17 | Create Skill set level Matrix Page - Functionality of Page | * SA should be able to create/modify the Skill Level Matrix. * Refer the Requirement Doc for complete details. |  | Rashi | 2014-09-09 | 2014-09-10 |  | In Progress |  | 152000% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 | 30 | 100 | 100 |  | 50 | 100 | 80 | 80 | 80 | 100 | 100 | 100 | 0 | 0 | 100
Prob_Form | 18 | Candidate Result Page - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Results can be emailed from this page. |  | Raunak | 2014-09-03 | 2014-09-05 |  | Completed |  | 200000% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 19 | My account | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Logged in Admins/SA can view my account page. * My account will have all the necessary details of the user like Oracle Id, Email, Phone, Career Stage, Profile Picture, etc. please follow psd's for other options. * By default user cannot modify Oracle Id and Email. * User can also change their password. |  | Arushi | 2014-09-03 | 2014-09-05 |  | In Progress |  | 157500% |  | 3 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 95 |  | 90 | 100 | 100 | 100 | 100 | 100 | 90
Prob_Form | 20 | Dashboard for Super Admin/ Admin | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * All Below Notifications should be opened inline on page in a Notification area on page. - New Question to Approve - Link will take to Question Listing page to approve - New Member request for approval - Link will redirect SA to respective listing page like HR/Interviewer listign. |  | Kunal | 2014-09-03 | 2014-09-08 |  | In Progress |  | 162000% |  | 4 |  |  | 100 | 100 | 100 | 100 | 75 | 95 | 100 | 100 |  |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 50 | 100
Prob_Form | 21 | Guideline/Instructions - Design the Page - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * On success login-in candidate will be redirected to guideline page. * Candidate shoujld be able to start test from this page. |  | Satyam | 2014-09-05 | 2014-09-05 |  | Completed |  | 170000% |  | 1 |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 41892 | 41892 |  | Amit Verma did the code reivew. Code review incorporations have been done.
Prob_Form | 6 | Manage Request Page - SA - Design the Page - Functionality of page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Email Notification should work for User on Approval or Rejection. |  | Kajal | 2014-09-10 | 2014-09-11 |  | In Progress |  | 160000% |  | 2 |  |  | 100 | 100 | 100 | 100 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Prob_Form | 22 | Take Test - Design the Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports * Display questions followed by options. * Display a timer of 30 sec. |  | Piyush | 2014-09-05 | 2014-09-05 |  | Completed |  | 0% |  | 1
Prob_Form | 23 | Take Test - Functionality of Page | * Designing Page as per given PSD's * Test the page on multiple browsers * Test the page on multiple view ports *Every 30 sec user will be prompted with a new question. User can submit there answer by clicking submit button. *If logged in candidate session expire, they should be able to resume from same question where they had left. * Disable the option box, post 30 sec. |  | Piyush | 2014-09-08 | 2014-09-09 |  | Completed |  | 0% |  | 2.5 | [24 empty] | 100
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
[7 empty] | #NUM! |  |  |  | 0%
#NUM!
Formulas:
End Date = IF(WORKDAY([Start Date],([Total LOE in days (ABP)]-1)) < [Start Date], WORKDAY([Start Date],([Total LOE in days (ABP)])), WORKDAY([Start Date],([Total LOE in days (ABP)]-1)))
Note on C11: [AB] this story is not required hence greyed out
Note on C18: WIN764BIT: [AB] dependency on the device list and UI left for this page. Depending upon Promil & Rahul's device list task else it will be over by 4 hrs
Note on C21: WIN764BIT: [AB] search functionality plus tables has sorting functionality and after clicking edit button it shows a form to edit device details; delete functionality hence taking time
Note on C54: [AB] this story is not required hence greyed out

## EAR (hidden)
NASCAR ¦ EAR : Steps of Doneness
S. No | Story | Status | Track | Owner Name | Start Date | End Date | % Complete | Total LOE in days (ABP) | LOE left to complete(days) | Understand the Use Case for EAR from India Arc | Identify any risk/issues/dep wrt to EAR and mitigation to resolve them | Design the EAR and close the approach with India Arc | Checkpoint with QA lead on testing approach for the EAR | Implement the EAR | Review with India ARC | Demo to offshore team | Deliver to QA track | Fix the defects | Demo to onshore team | Demo to Clients | Mention any loose/open points in the EAR Document | Delivered Quality
[10 empty] | 5% | 5% | 10% | 5% | 40% | 10% | 5% | 3% | 5% | 2% | 5% | 5%
1 | [6 empty] | 100% |  |  | y | y | y | y | y | y | y | y | y | y | y | y
2 | [6 empty] | 10% |  |  | y | y
3 | [6 empty] | 0%
4 | [6 empty] | 0%
5 | [6 empty] | 0%
6 | [6 empty] | 0%
0%
Track Status
Weekly Milestones
1
2
3
4